## Slide 1: Mojaloop Deployment and DFSP Onboarding experience in Myanmar (Hub Operator’s perspective)
07.03.2023
Pyae Phyo Lwin
ThitsaWorks

## Slide 2: Preparation for Mojaloop Deployment

## Slide 3: Team Setup
Setting up organization structure of Hub Operator (Business, Technical and Operations) with phase by phase basics
Preparation of Job Scope for each position
Recruitment of needed position
Training team members with Mojaloop training materials
Collecting and distributing resources from similar systems

## Slide 4: Readiness for Onboarding
Learn API standard format between Hub, Payment Manager and the backend system of DFSPs
Prepare the possibility of scheme rules ahead like a "multiple-of" value handling process, data privacy/confidentially process and fee structure
Define the testing phases (e.g. Friendly User Testing - FUT, Closed User Group - CUG) before the scheme commercially goes Live
Define the workflow and process for each use cases
Develop the onboarding checklist and guideline
Create a test plan for integrated testing and end-to-end testing
Communicate with tech team for development of each use cases

## Slide 5: Readiness for Settlement
Make agreement of settlement steps between hub operator and settlement bank
Define the Net Debit Cap (NDC) and minimum balance of liquidity account
Define the scheduled settlement time
Develop SOP for daily settlement process
Develop the required report specification for the daily settlement processes
Learn the finance portal to familiarize the settlement process

## Slide 6: Readiness for Customer Service
Create service desk portal
Define general issue types to add in portal
Prepare service desk user guideline
Prepare support service workflow (SLA agreement, whole support flow diagram, support level etc.,)
Prepare the agenda for service desk training to DFSPs
Develop SOP for customer service process

## Slide 7: Experience of Onboarding DFSPs

## Slide 8: Onboarding Steps
Discuss with DFSP to learn and understand their business workflow
Discuss with DFSP’s Technical team for API Integration
Test DFSP’s backend system APIs with postman
Conduct the feasibility check with Internal technical team
Produce integration specifications including workflow, business rules, mappings and API calls
Engage DFSP for payment manager portal accounts and to verify 2FA set up
Engage DFSP for the demonstration of payment manager portal
Conduct integrated testing
Conduct end-to-end testing

## Slide 9: Onboarding Challenges
MFI
  Phone number standard format in MFI backend system
  Repetitive tasks like credentials and payment type creation when the restore process in MFI’s core banking system
  Re-communicate with MFI for Incorrect payment type configuration (Payment type deletion (or) renaming in MFI’s core banking system)
Wallet
Lack of Amount reserved feature (2-phase commit) – causes frequent refund process
Communication challenge on requesting repetitive tasks regarding the changes in MFI logos and names
Common
Require proper guidance on clear understanding of DFSP’s API documentation

## Slide 10: Onboarding timeline and documents
  MFI – From 3 to 6 months
  Wallet – From 1 to 6 months
  SOP for onboarding, settlement and customer service
  Error Handling
  Assessment form to collect basic information of wallets
  Transactions Report (FUT)
  WynePay Brand Guideline for Wallet Providers
  Dispute Management Document Version 2
  Risk Management Framework and Risk Registry
Onboarding Timeline
Documents

## Slide 11: Settlement Steps
Prepare settlement process work flow
Arrange a meeting with DFSP to explain Settlement Process
Support DFSP to open the Liquidity account at Settlement bank
Request the contact information of DFSP to inform daily settlement completion process
Create the user account in Document Management System for keeping the settlement report
Open the group chat with each DFSP and Settlement bank via Skype or Viber
Monitor the DFSP liquidity balance according to the updated balance mail sent by the settlement bank
Do daily settlement

## Slide 12: Customer Service Steps
Open communication channel with DFSPs (Skype)
Do daily support process as per agreed SLA
Prepare Dispute Management Process (Dispute principals, scenarios etc.)
Prepare Dispute Report Specification and Format
Prepare Risk Management document

## Slide 13: Customer Service Challenges
Submit incomplete information of ticket escalated by DFSPs.
Conduct back-and-forth communication through the channel (Skype) for incomplete information from the DFSPs.
Depend on DFSPs for Dispute Process (impact on agreed SLA for resolution)

## Slide 14: Lesson Learned from Friendly User Testing (1.0 & 2.0)

## Slide 15
Friendly User Testing (FUT)
FUT – Phase 1
FUT – Phase 2
Period : 30 Sep 2021 - 31 March 2022
Use Case readiness : Repayment
Participants : 5 (3 MFIs and 2 Wallets)
Total transactions : 336
Period : 6 June 2022 - Current
Use Case readiness : Repayment, Disbursement
Participants : 8 (4 MFIs and 4 Wallets)
Total transactions : 117

## Slide 16
Lessons learned from Friendly User Testing
Insufficient liquidity of DFSPs
Insufficient balance error (Wallet has limited minimum balance of 1000Ks in the client’s wallet)
Amount edition in Wallet
Certificate expiration
Wallet 5-minute business rule
API issue
PVC issue related to TechOps
Credentials permission
Core Banking System EOD/EOM process
Connection issue
Incorrect Payment Type configuration
Incorrect Core Connector configuration
Issue related with wallet update version

## Slide 17
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Wallet Provider checks only Response for HTTP Request in API integration
One of the wallet tech team configured staging core connector link in PROD
Checking the standard API response code (HTTP) is not enough to differentiate the transaction status
Need to check the error scenarios with dummy data as soon as an DFSP onboarded in PROD environment.
Though the standard response for successful HTTP request is returned, the transaction status in the response of API body is “Aborted”. For not checking the status in the body on the wallet side, the transaction is shown as successful one in the wallet UI and the transaction amount is deducted from the wallet balance. But in HUB and MFI side, the transaction is failed.
When the user makes the transaction with prod wallet app, they cannot proceed with the testing and face with timeout error
Hub operation team requests the wallet providers to check the transaction status in the response of API body as one requirement of the integration process.
Hub operation team added a step in onboarding plan to check the error scenarios with dummy data as soon as an DFSP onboarded in PROD environment.
Improvement
Impact

## Slide 18
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Service Desk Portal Labels and Parameters
Realize that the missing out labels can give wrong analysis on monthly report generation
Aware that the high level RCA is not enough to explain the error
Showing incomplete data insights and analysis on monthly report due to the lack of parameter in Service Desk Portal
High level explanation without much details causes confusion and misunderstanding on the exact root cause of the error.
The support engineers added as new step in SOP to take responsibility for filling out labels and related parameters in the tickets.
The precaution has been setup in the team to provide a complete root cause analysis report to the DFSP.
Root Cause Analysis (RCA)

## Slide 19
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Transactions fail during EOD and EOM process of Core Banking System (Flexcube)
Mail notification is not enough to inform MFI when there are new updates regarding WynePay
Aware of the transaction failing reason due to the MFI’s EOD and EOM process in Core Banking System
Sometimes DFSP needs to be informed by more than one communication channel to be aware of certain upgrades and news (e.g., when new wallet joins to WynePay)
Though the user made the repayment transaction with correct information, the transactions is not posted on MFI side. But the transaction amount was deducted from the wallet balance. Thus, we need to engage with wallet providers for the refund processes.
Recently, one of the MFI was not aware of Hub operator’s mail regarding new wallets onboarded in PROD environment, resulting transaction failure due to the lack of payment type setup in MFI side.
Hub operation team requested the wallet providers to deduct the transaction amount after receiving the successful API response from HUB at the transfer phase since one of the MFI CBS (Flexcube) is not able to allow the transactions during EOD and EOM process.
Hub operation team informed not only via email but also via Skype so that every DFSP is informed when a new wallet joined to WynePay and created the required configuration in CBS for making the transactions.

## Slide 20
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Certificate Expired
Certification expiry notifications on slack is not enough, since failing the slack notification job results in not aware of the expiration alerts.
Causes transaction to be failed in every DFSP
Implemented certification expiry alerts to get alerts on both slack channel and email calendar notifications. This issue has been also prevented by upgrading the hub to version 14.1.0, which includes the auto cert-renewal feature.

## Slide 21
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Finance Portal Cache Issue
DFSP liquidity account details are missing in the settlement bank report.
Realize the caching issue can cause a huge impact on the settlement process.
Some of the information in the settlements reports are hardcoded which needs to be updated when there is a new DFSP onboarded, it is hub operator’s responsibility to make sure that. (e.g. liquidity account for DFSP)
Cashing causes the settlement finalization process to hung resulting funky behavior on DFSP financial position. (e.g. Window not settled although position amount has been updated or settled without updating the financial position.
Causes delay in settlement process
The product delivery team identified this as a Mojaloop based caching issue and the current work around is to clear cache or use private browser for settlement process.
Hub operation team added a new step in onboarding checklist to communicate with DFSP about liquidity account information and provide it to internal dev team to be able to display it on reports.

## Slide 22
Lessons learned
Project Parameter
Lesson Learned
Impact
Improvement
Changes in liquidity balance (adding or withdrawing)
Need discussion and communication about the procedures in advance with settlement bank to inform the liquidity changes in DFSP
Causes balance and NDC difference between settlement bank and finance portal.
As automation alert for liquidity changes are not implemented yet, hub operation team engages with settlement bank to send the balances of DFSP on a agreed time slots (4 times) to reduce the liquidity risk.

## Slide 23: Thank you!
thitsaworks.com
info@thitsaworks.com
Fb.me/thitsaworks